TVP Reference PR23018
PCC 2024 / 024

Contract for the supply of

Design and Build of a New Logistics Hub

Gateway C: Commercial Outcome Report & OPCC Decision Report

Submitted By: Dan Penny

Date Submitted: 27/11/2024

# Contract Award (and COR) Sign-Off Sheet

It is the responsibility of the Procurement Department to complete and present this paper to the CGB (this may be by a virtual process)

By approving this document the Commercial Governance Board confirms acceptance of the detail contained within this document, approval to proceed with contract award, implementation and realisation of the benefits.

In the case of a Procurement which results in a new contract (or extension) the document replaces the previous award paper, and has a section for the relevant sign-offs below.

Part 1 –
For publication on TVP / PCC Internet Site

Public access to information
The information in this COR is subject to the Freedom of Information Act 2000 (FOIA) and other legislation. Part 1 of this form will be made available on the website within 1 working day of approval. Any facts and advice that should not be automatically available on request should not be included in Part 1 but instead on a separate Part 2 form. Deferment of publication is only applicable where release before that date would compromise the implementation of the decision being approved.

Executive Summary and Recommendations
Background: Current / Baseline / Budgeted Spend - (Total spend £45m - £50m in two contracts. Contract 1 – PCSA circa £1.25m (issued at tender release) and increased to £1.69m post tender submission and contract 2 – Construction for the remaining circa £48m) £50m / This Commercial Outcome Report (COR) records the Enabling Services element of the process as approved for the design and build of a new Logistics hub for Thames Valley Police and should be read in conjunction with the approved Commercial Launch Document (CLD) from November 2023 and the Commercial Outcome Report (COR) from March 2024. / Summary of requirement: In November 2023, Thames Valley Police (TVP) commenced a two-stage process for the design and build of a new logistics hub. The commercial strategy is for a two-stage process, the first for the early stage contractor services under Pre-Construction Services Agreement (PCSA) and the second for the construction of the new logistic hub subject to competitive package tendering under the PCSA and final costs approval. / This commercial evaluation report is seeking the approval of the Enabling Works element of this contract based upon the procurement strategy undertaken. / Summary of Procurement Process: The agreed procurement process as per the CLD was to carry out a Mini Competition under the Southern Construction Framework (SCF) for the early stage contractor services under Pre-Construction Services Agreement (PCSA) and ultimately the construction of the new logistic hub subject to competitive package tendering under the PCSA and final costs approval. / A fixed price lump sum offer for enabling works was issued by MS on 30.09.24. A commercial overview of the original MS submission is included within the below table: / Ref Element £ / 1 Tree Protection Fencing £24,733 / 2 Groundworks £6,702,389 / 3 Site boundary works £692,928 / Work Package - Sub-Total £7,420,050 / 4 Preliminaries £1,332,246 / Sub-Total £8,752,296 / 5 Design Fees £30,546 / Sub-Total £8,782,842 / 6 Design & Build Construction Risk – at 3% £263,485 / Sub-Total £9,046,328 / 7 Overheads & Profit – at 5.25% £474,932 / Sub-Total £9,521,260 / 8 Undefined Provisional Sums £220,000 / Total Enabling Works Tender Offer (Excl VAT) £9,741,260 / It had previously been reported to key project stakeholders that the program would be seeking approval for an enabling works contract sum in the range of £6m-£7m. It was agreed that the current scope of the enabling works offer was too comprehensive, including for elements of the Groundworks package which went further than site clearance/preparation. In addition, the sub-contract returns for one of the packages, site attenuation, were significantly over budget. A value engineering exercise on this package needed to be undertaken before this work could be instructed. / MS were asked to review their fixed price offer and to exclude any elements which were not originally identified to form part of the enabling works scope. / A revised enabling works offer was received on 02.10.2024. A commercial overview of the revised MS submission is included within the below table: / Ref Element £ / 1 Tree Protection Fencing £24,733 / 2 Groundworks £3,485,003 / 3 Site Boundary Works £572,750 / Work Package - Sub-Total £4,082,486 / 4 Preliminaries £1,130,131 / Sub-Total £5,212,617 / 5 Design Fees £30,546 / Sub-Total £5,243,163 / 6 Design & Build Construction Risk – at 3% £157,295 / Sub-Total £5,400,458 / 7 Overheads & Profit – at 5.25% £283,524 / Sub-Total £5,683,982 / 8 Undefined Provisional Sums Excluded / Total Enabling Works Tender Offer (Excl VAT) £5,683,982 / Key notes / Regulation 84 form has been completed and is at Appendix A (Note that by default a regulation 84 form should be completed in all circumstances). This is a record of the exercise required to be kept by the Cabinet Office. / Contract Terms and Conditions: The suppliers meet all the requirements of the contract terms and conditions and specification and offer the Most Economically Advantageous Solution, as assessed through the evaluation process. / Legal Implications: This contract has been awarded by a legally compliant methodology / Equality and Diversity: There are no specific issues with regard to Equality & Diversity with this award. / Social Value: There are no social value initiatives directly associated with this bid / Realisation Implementation Plan. Implementation plan for the new contract will be discussed and agreed on contract award. / Contract Management Review: Tier 1 or Tier 2 or Tier 3 / The procurement process has followed and complied with the 5 key Treaty Principles of PCR 2015:- Transparency; Non-Discrimination; Equal Treatment; Proportionality; Mutual Recognition. / There is a confidential Part 2 form is for internal use and is not for publication into the public domain due to the sensitive/commercial nature of the information

# 2. Attachments
Please include the following attachments as additional supporting information:
 Any additional Supporting information
# 3. FINANCIAL IMPLICATIONS
This project is funded entirely by a grant from the Home Office / The break-down of each subcontract package is shown in the Enabling Services Report in Section 2

# 4. RECCOMENDATIONS
The Police and Crime Commissioner / Chief Constable of Thames Valley Police (Chief Finance Officer and Director of Finance) are invited to agree the award of Enabling Servies element of the contract in respect of the above to Morgan Sindall. / The sub-contract tender process undertaken by MS is in accordance with the process outlined within the PCSA. MS have provided sufficient competition for each package to provide adequate market testing and the process has been undertaken on an “open book” basis. It is noted that there remain some commercial clarifications that are still to be finalized, however these are not noted to be significant in nature. It is our recommendation that the offer from MS is taken forwards to form the basis of the enabling works contract.

Process and COR approval
Role	Name/Job Title/or Shoulder No.	Signature and Sign-Off Date
Project Sponsor (Stakeholder) / Approving the proposal as meeting the requirements	Tim Metcalfe	27 November 2024
Procurement Business Partner / Approving the award as meeting the commercial and regulatory requirements of the force	A Hughes	28.11.24
Procurement Lead / Confirming the process as meeting the objectives and regulatory requirements set	Dan Penny	28/11/2024
TVP Finance / Confirming that they have approved the budgetary and financial implications of this proposal	Karen Ackland (C1409) Finance & Services Business Partner	K M Ackland / 28/11/24
Legal (If applicable) / Confirming their review of any legal implications of this proposal	N/A	N/A

Approval Role	Name or Shoulder Number	Job Title	Signature and Sign-Off Date
Approver / Supporter / approving contract award up to a value of £200,000 and supporting values above £200,000	Richard Fowles	Head of Procurement	28/11/24
Approver / Supporter: / approving contract award up to a value of £1,000,000 and supporting values above £1,000,000	Linda Waters	Director of Finance	02/12/24
Consulted / Approver: / Consulted on contract award values of £200,000 up to £1,000,000 / Approval on contract award values above £1,000,000	Martin Thornley	OPCC - Chief Finance Officer	29/11/24
Approver: / Approval on contract award values above £1,000,000	Martin Thornley in Gillian Ormston’s absence	OPCC – Deputy Chief Executive on behalf of Chief Executive	29/11/24
Final Approver: / Approval on contract award values above £1,000,000	Matthew Barber	Police & Crime Commissioner	29/11/24

Contract Summary and Information for BLPD
Proposed Supplier (s)	Morgan Sindall
Planned Contract Start Date	April 2024
Contract Duration – Initial Term (months)	8 months PCSO, 20 months Construction
Contract Extensions Available (months)	N/A
Contract Value Initial Period (months)	N/A
Contract Value Extension per extensions periods	N/A
Collaborative Purchase Information (who are we buying with and what is there proportion of spend).	N/A

Contract Savings (for use on Home Office benefits reporting – NOT TO BE INPUT ON BLPD)
Baseline Spend (highlight any changes to information provided in CLD)	N/A
Savings Enabled: / Detail at High, Low and Expected level if the savings are likely to be variable e.g. based on demand. / Include Annual & Total Contract Savings	Cashable:£N/A / Plus Commentary on what these savings represent (eg against existing or negotiated against initial quote / tender bid)
	Please indicate if renewal of existing contract or a new requirement purchase.
Savings Start Date if different from Contract start date	Cashable:£N/A / Plus Commentary on what these savings represent (eg against existing or negotiated against initial quote / tender bid)
Collaborative Savings	Please indicate if renewal of existing contract or a new requirement purchase.
Savings Types (based on Savings Definitions in Savings Analysis Worksheet)	Cashable:£N/A / Plus Commentary on what these savings represent (eg against existing or negotiated against initial quote / tender bid)
Other Benefits:	Please indicate if renewal of existing contract or a new requirement purchase.
Total Savings as a % of baseline spend:	Cashable:£N/A / Plus Commentary on what these savings represent (eg against existing or negotiated against initial quote / tender bid)